## Original Tasks (hidden)
Workstream | Category | Sub Channel | Task | Mutual Resources | S1 Resources | Timing | Start Date | End Date | Additional FTE
BSA / Fraud | Program |  | Bank needs to incorporate S1 Lending into the existing program | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | Program |  | Onsite Risk Assessment Meeting at S1 - Conduct Due Diligence by Bank's BSA Officer | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | Monitoring |  | S1 to provide customer list to incorporate into Bank's FiServ OFAC check. Determine S1 OFAC match %. | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | Policies |  | S1 to determine if they are identifying PEPs and if not, incorporate PEP identification into their process and procedures | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | Procedures |  | Enhance existing procedures to outline OFAC escalation and how discrepencies are remediated. | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | CIP |  | S1 to provide Bank CIP / KYC underwriting guideline documentation | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | External Reviews |  | Currently a BSA/AML audit going on right now, requested by S1 to be completed. The Compliance Group is conducting the audit. | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | Procedures |  | S1 to formalize SAR filing procedures to include reporting process | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
BSA / Fraud | CIP |  | S1 to send non resident alient guidelines to Vinay | Vinay Madar | David Entrekin | Completed | 2018-05-10 | 2018-05-10
BSA / Fraud | Program |  | Incorporate S1 into the Bank's BSA/Fraud Program | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01 | 0.25
BSA / Fraud | Program |  | Determine S1 SAR filing threshold and identify gaps including VOD/VOE discrepencies | Vinay Madar | Eric Jones | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Program |  | Determine how many SARs were filed by S1 in the past 12 months | Vinay Madar | Eric Jones | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Program |  | Bank to begin receiving SAR filing reports from S1 | Vinay Madar | Eric Jones | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Policies |  | Determine if each of the policies are sufficient based on mortgage company vs. deposit institution. Determine if they can remain separate or combined. | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Monitoring |  | Mutual to determine if S1 processes can go through FCRM or other software systems | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Policies |  | Bank to scrub S1 customer list against 314.A list | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Risk Assessment | BSA | Bank to incorporate S1 into BSA risk assessment | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Risk Assessment | Fraud | Bank to incorporate S1 into Fraud Risk assessment | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Training |  | Strengthen S1 training with the deployment of Bank eLearning courses for BSA & Fraud. Determine when to roll out new training to S1 employees. | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Training |  | Add training reconciliation and tracking of S1 training completed and ongoing basis to the Bank's tracking process. | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Training |  | Align test passing score with that of the bank. | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Training |  | In addition to eLearning, participation in the Bank's annual Mortgage Fraud and BSA Training webinars will be required. | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Training |  | communicate to S1 employees all enhancements made related to BSA/Fraud | Vinay Madar |  | Optimization | 2018-07-01 | 2018-10-01
BSA / Fraud | Monitoring |  | The point of contact will need to be changed to DG-Fraud investigation and DG-BSACompliance going forward | Vinay Madar |  | Optimization | 2018-07-01 | 2018-10-01
BSA / Fraud | Monitoring |  | Identify BSA/Fraud monitoring tools utilized by Synergy 1 today. Will they continue to use the same systems? Do they have documented processes to ensure fraud and/or suspicious activity is escalated to their internal point of contact? | Vinay Madar |  | Optimization | 2018-07-01 | 2018-10-01
BSA / Fraud | Personnel |  | Assess adequasy of staffing for BSA/AML | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01 | 1
BSA / Fraud | Board Reporting/Communication |  | Incorporate S1 intot he Bank's reporting to the board | Vinay Madar |  | Optimization | 2018-10-01 | 2019-01-01
BSA / Fraud | Test Plan/Testing |  | S1 to provide The Compliance Group final report to Bank's BSA Officer for review. BSA Officer to determine if additional testing needs to occur | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Test Plan/Testing |  | Bank Internal Audit will conduct annual independent audit of BSA/AML | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01 | 0.25
BSA / Fraud | Ongoing Oversight |  | Bank in process of developing oversight process | Vinay Madar |  | Optimization | 2018-07-01 | 2018-09-01 | 0.25
BSA / Fraud | BSA Officer |  | Document the transition of S1 BSA Officer from Bill to Vinay Madar via S1 Board Approval Meeting Minutes | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Reporting |  | S1 to provide business BSA line reporting to Vinay. | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Reporting |  | Determine process for S1 to notify the Bank's BSA Officer if any S1 subpoenas are receievd. | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | CIP |  | Bank's BSA Officer would like to see QA/BSA items to be sure that CIP is covered and escalated | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Procedures |  | Align S1 procedures with Bank BSA procedures for retail mortgage and correspondent mortgage | Vinay Madar |  | Optimization | 2018-07-01 | 2018-08-01
BSA / Fraud | Personnel |  | S1 to identify an internal resource for ongoing Mortgage specific BSA and Fraud Training | Vinay Madar |  | Optimization | 2018-07-01 | 2018-10-01 | 0.25
Capital Markets | Hedging |  | S1 to send Mutual hedging policies | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Lock Desk |  | S1 to provide Mutual standard pipeline report | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Capital Markets | Lock Desk |  | Mutual to review S1 standard pipeline report to understand position | Andrew Tetlow |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Capital Markets | Investor Relationships |  | Mutual to send S1 contact information for Kelly Collins and John Matuszeski for Clink setup | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Capital Markets | Investor Relationships |  | Mutual to send S1 investment policy | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Capital Markets | Credit | Legal | Update bank credit matrix to include reverse mortgage thresholds | John Cox |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Credit |  | Determine if Mutual of Omaha Bank lending authority should be updated or adjusted to include S1 executive team | John Cox |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Investor Relationships |  | S1 and Mutual to setup 2 separate seller service numbers (Fannie, Freddie, etc) | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Investor Relationships |  | S1 to provide notice to sellers/investors (Fannie, Freddie, etc.) | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Investor Relationships | Forward Mortgage | Mutual to submit application for Ginnie Mae for Mutual - forward | Andrew Tetlow | Ken | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Investor Relationships | Reverse Mortgage | Mutual to submit application for Ginnie Mae for S1 - forward | Andrew Tetlow | Ken | Prior to Day 1 | 2018-05-10 | 2018-07-01
Capital Markets | Margin Management |  | Build and consolidate into a common margin framework; aligned by business groups, branches and regional pricing |  |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | Address acquistion with all investors and combine overlapping investors. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | Will have two separate seller servicers numbers with Fannie /Freddie. Reach out of the Fannie/Freddie reps to give an update on our merger and how this looks post close. Notice requirements & communication to all investors including Fannie/Freddie. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Ginnie Mae |  | MOOB is currently not Ginnie Mae approved and steps to get this completed needs to be initiated. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Ginnie Mae |  | S1 is only approved for Reverse for Ginnie Mae. Steps to get them approved for forward needs to be initiated. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Investor Relationships |  | Will need to determine which balance sheet to have these sit on (S1 or MOOB) then submit the appropriate paperwork. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | Contract requirements and servicing elements need to be determined (work with Bank Correspondent) and add to the top 30 EVMP vendor list. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | MOOB needs to touch base with Fannie to let them know we may begin using them again. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | MOOB needs to touch base with Freddie to let them know we may begin using them again. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | MOOB needs to touch base with Redwood to let them know we may begin using them again. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | MOOB needs to touch base with additional investors to let them know we may begin using them again. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-09-01
Capital Markets | Investor Relationships |  | Mutual to review placement of balance sheet - preference to hold on the Bank | Andrew Tetlow |  | Optimization | 2018-08-01 | 2018-09-01
Capital Markets | Investor Relationships |  | Mutual to pursue getting forward and reverse in place for the bank; and for S1 | Andrew Tetlow |  | Optimization | 2018-08-01 | 2018-09-01
Capital Markets | Warehouse Line Funding |  | Transition loan warehouse funding to lower cost Bank funding though a self-funded warehouse line. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Warehouse Line Funding |  | Consolidate for financial purposes and complete the proper paperwork to complete. Separate project meeting, set up by Andrew, with key perssonel to determine all affected channels and divisions. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Warehouse Line Funding |  | Determine which warehouse lines are up for renewal and how to handle those. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Warehouse Line Funding |  | Determine if seperate lines should be left specific to certain products. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Warehouse Line Funding |  | Mutual and S1 hold a call to ensure aligned on S1's conversations with Everline | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Warehouse Line Funding |  | Mutual and S1 to discuss warehouse lines that are up for renewals | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Loan Servicing for Investors |  | Transition Synergy loan sales from primariliy "servicing released" to primarily. *releated to Ginnie Mae | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-10-01
Capital Markets | Loan Servicing for Investors |  | Determine moving the MSRs and how to approach that. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-10-01
Capital Markets | Reverse Mortgage Portfolio Product for Bank |  | Teams should work to develop a portfolio product to be held and serviced on the Bank balance sheet. Develop participation arrangement with Mutual Insurance teams to cover longevity tail risks. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-07-01
Capital Markets | Reverse Mortgage Portfolio Product for Bank |  | Mutual to create a portfolio reverse product framework; investigation | Andrew Tetlow |  | Optimization | 2019-01-01 | 2019-12-01
Capital Markets | Reverse Mortgage Portfolio Product for Bank |  | Mutual and S1 to discuss Federal Home Loan Bank relationship and how to optimize for S1 | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Reverse Mortgage Portfolio Product for Bank |  | Mutual and S1 to discuss fundings through x dates and then slowly transition to the Bank's warehouse lines. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Reverse Mortgage Portfolio Product for Bank |  | Mutual and S1 to discuss keeping on warehouse lines for additional products | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Pricing | Forward Mortgage | Mutual needs to fully understand S1 pricing by channel - Forward | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Pricing | Reverse Mortgage | Mutual needs to fully understand S1 pricing by channel - Reverse | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Pricing |  | S1 to send Mutual a margin matrix to review | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Pricing | Reverse Mortgage | S1 to provide margin framework to Mutual for them to optimize | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Pricing |  | Mutual to determine a plan on how to integrate consumer direct as another branch | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-11-01
Capital Markets | Hedging |  | Mutual to review S1 hedging policies to determine if they need to match or be separate. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-08-01
Capital Markets | Hedging |  | S1 to send management reporting for hedging ongoing to lockdesk@mutualofomahabank.com | Andrew Tetlow |  | Optimization | 2018-08-01 | 2019-01-01
Capital Markets | Lock Desk |  | S1 to email lockdesk@mutualofomahabank.com a standard pipeline report every Friday | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-10-01
Capital Markets | Margin Management |  | Steve will make market adjustments to increase margin | Andrew Tetlow |  | Optimization | 2018-07-01 | 2018-10-01
Capital Markets | Margin Management |  | TPO sales group will send competitor rate sheets weekly to lockdesk@mutualofomahabank.com | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-01-01
Capital Markets | Margin Management |  | Mutual to download into "One Comparison" against peers. | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-01-01
Capital Markets | Margin Management |  | S1 to track, monitor and maintain competiveness | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-01-01
Capital Markets | Investor Relationships |  | Mutual to work with S1 to setup CLInk monitoring requirements and documentation | John Matuszeski |  | Optimization | 2018-06-01 | 2018-08-01
Compliance 1st LOD (S1) | Regulation O |  | Determine process to monitor applications by insiders | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Regulation O |  | Incorporate Reg O process into S1 procedures | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Regulation O |  | Define ongoing reporting and comparison with the Bank's reportweekly query. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Vendor Management |  | S1 to formalize and implement Vendor Oversight Program | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Issue Management |  | S1 to formalize issue management program and monitoring | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Issue Management |  | S1 to provide issue management tracking to Bank Ops Risk Management monthly for oversight for escalation as deemed necessary | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Training |  | S1 to strengthen consequences at S1 for non-compliance |  |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Complaints |  | S1 to monitor broker performance and determine a plan to enhance performance and customer service | Jessica Staudt |  | Optimization | 2018-07-01 | 2019-01-01
Compliance 1st LOD (S1) | Complaints |  | Widen S1's complaint capture net (ie: capture resolved complaints) | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Complaints |  | Incorporate a referral element for escalation of possible Fair Banking related complaints to the Bank's Fair Banking Manager. | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Complaints |  | Enhance S1 complaint tracking spreadsheet to include all Bank JIRA complaint elements for easy uploading | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Complaints |  | Establish specific Broker performance scorecard and identified escalation elements. | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Procedures |  | Bank to evaluate current job aids and procedures to determine if enhancements are needed | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Checklist |  | Bank to evaluate checklists to determine if enhancements are needed | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Remediation |  | Bank to determine process to track/document and monitor issues from audit, QA, QC, complaints, vendor and broker oversight and the resolution to those issues | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Key Risk Indicators |  | Determine if any KRI's are being captured today | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Key Risk Indicators |  | Determine what KRI's should be developed for reporting | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Key Risk Indicators |  | Evaluate what S1 KRI's S1 reports to their board today | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Risk Assessment |  | S1 is currently developing a risk assessment | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Personnel |  | Evaluate current S1 employees with a Compliance role to determine their roles going forward in either a 1st line or 2nd line function | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Personnel |  | S1 to hire 1 FTE - QC | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Compliance 1st LOD (S1) | Personnel |  | S1 to hire 1 FTE - QA | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Compliance 1st LOD (S1) | Personnel |  | S1 to hire 1 FTE - NMLS | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Compliance 1st LOD (S1) | Personnel |  | Determine Bill's current role / responsibility and which elements are 1st LOD and which are 2nd LOD and what elements need to be transitioned to another employee and/or brought into the Bank. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Reporting |  | S1 to determine what additional reports can be generated for compliance monitoring | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Quality Control (QC) | Reverse Mortgage | Create QC testing function for Reverse Mortgage | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Quality Control (QC) | Forward Mortgage | Create QC testing function for Forward Mortgage | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Quality Control (QC) |  | Develop QC checklists | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Quality Control (QC) |  | Develop scorecards for QC results | Jessica Staudt |  | Optimization | 2018-09-01 | 2018-10-01
Compliance 1st LOD (S1) | Quality Control (QC) | Reverse Mortgage | Ensure QC Analyst receives reverse mortgage training | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | HMDA QA |  | S1 to develop Source Doc Matrix with Bank assistance | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Broker Oversight |  | S1 to develop scorecards for broker monitoring | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Broker Oversight |  | S1 to determine reporting for scorecards | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Complaints |  | S1 to incorporate Bank's complaint definition, policy and procedure | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 1st LOD (S1) | Complaints |  | S1 to provide training to staff on new complaint process | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 1st LOD (S1) | Complaints |  | S1 to analyze complaints for root cause analysis and appropriate closure then send to the Bank Compliance for review | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 1st LOD (S1) | Complaints |  | S1 to provide key metrics to S1 upper management | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 1st LOD (S1) | Training |  | Determine if any additional training is required (ie; Ethics, Code of Conduct, New Hire Training, etc.) | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Training |  | S1 to provide Bank with training attendance log monthly | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 1st LOD (S1) | Advertising & Marketing |  | Discuss and determine S1's Marketing Plan and Strategy and volume (including stock ads) | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 1st LOD (S1) | Advertising & Marketing |  | Determine what advertising materials need enhanced based on purchase/product | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 1st LOD (S1) | Change Control |  | S1 to provide Bank with current change control process | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Compliance 1st LOD (S1) | Social Media and Web Monitoring |  | S1 to provide Bank with detailed outline of how S1, lenders and brokers, utilize social media to generate business | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Social Media and Web Monitoring |  | S1 to streamline S1 social media marketing pushes so they are all through a centralized non-LO department | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 1st LOD (S1) | Flood |  | S1 tp update flood procedures and checklists where applicable | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Advertising Review |  | Determine if Bank Terradata system should be used for S1 Fair Lending marketing pieces in the future. | Matt Bunting |  | Optimization | 2018-10-01 | 2019-01-01
Compliance 2nd LOD (Bank) | Advertising Review |  | Identify if S1 needs a Bank laptop to complete ad reviews to enter data into Teradata marketing system | Matt Bunting |  | Optimization | 2018-10-01 | 2019-01-01
Compliance 2nd LOD (Bank) | Advertising Review |  | Bank to complete spot checks of advertisements prior to release |  |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Advertising Review |  | Bank Legal to determine language to be included on ads regarding relationship |  |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Broker Oversight |  | Evaluate current broker oversight program | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Broker Oversight |  | Incorporate additional elements from A&M report such as funded units, volume, average FICO, average LTV, funded with errors and omissions, etc. | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Broker Oversight |  | Determine additional elements to be added to oversight program | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Change Control |  | Bank to determine process to ensure compliance change control items are reviewed and tracked for impact (ie: system updates, regulation changes) | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Change Control |  | Bank to evaluate S1 change control procedure | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Complaints | Fair Banking Program | Bank to obtain listing of S1 customer service surveys and conduct analysis | Jessica Staudt |  | Optimization | 2018-07-01 | 2019-01-01
Compliance 2nd LOD (Bank) | Complaints |  | Provide S1 taining on Bank complaint tracking expectations | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Complaints |  | Bank to assist S1 with creation of complaint process training materials | Jessica Staudt |  | Prior to Day 1 | 2018-05-15 | 2018-06-01
Compliance 2nd LOD (Bank) | Complaints |  | Bank to determine process for incorporating S1 complaints into the Bank's Jira system for tracking purposes | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 2nd LOD (Bank) | Complaints |  | Identify current process for S1 to review complaints for trending and reporting | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Complaints |  | Determine process to capture broker complaints | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Flood |  | Flood Ins. payment via the HUD documentation may not regulatory sound and the process today on Day 1 may need to be changed to include actual proof of payment along with copy of insurance application. May inpack the broker community and production volumns. Bank Compliance will research this further and set up follow up meetings with key SME to discuss further. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Flood |  | Determine if escrow rules for flood apply to any of the S1 product lines | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Flood |  | Bank to implement changes based on flood review findings from due diligence review | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Flood |  | Bank to provide training to S1 employees by Bank Compliance | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | HMDA |  | Evaluate HMDA QA process and assist in developing source document matrix | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | HMDA |  | Discuss and document HMDA LAR submission processes | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-11-01
Compliance 2nd LOD (Bank) | HMDA QA |  | Bank to evaluate HMDA QA program and procedures | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Key Risk Indicators |  | Incorporate S1 KRIs into Bank Reporting Package | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Management Compliance Committee |  | Determine, if deemed necessary, who from Bank or S1 will represent S1 at Bank Compliance Committee | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | New Products & Services |  | Determine S1 new product and services procedure including; S1 new product committee reporting |  |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | New Products & Services |  | Bank to evaluate if we integrate new product processes |  |  | Optimization | 2019-01-01 | 2019-02-01
Compliance 2nd LOD (Bank) | New Regulation Implementation |  | Determine what state law and regulatory changes are impacted by the purchase | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | New Regulation Implementation |  | Bank to begin incorporating S1 (Bill) into Bank regulation change meetings | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Oversight |  | Bank to identify how to access loan documentation to use for 2019 review | Jessica Staudt |  | Optimization | 2019-01-01 | 2019-02-01
Compliance 2nd LOD (Bank) | Personnel |  | Bank to hire 1 FTE - location TBD for Testing/Compliance Reviews |  |  | Optimization | 2018-07-01 | 2018-08-01 | 1
Compliance 2nd LOD (Bank) | Personnel |  | Evaluate current S1 employees with a Compliance role to determine their roles going forward in either a 1st line or 2nd line function | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Personnel |  | Bank to assess Rick Harm's role in 1st line of defense oversight | Jessica Staudt |  | Optimization | 2018-06-01 | 2018-07-01
Compliance 2nd LOD (Bank) | Procedures |  | Bank conduct an inventory of all S1 active procedures; including last review date. | Jessica Staudt |  | Optimization | 2018-10-01 | 2018-12-01
Compliance 2nd LOD (Bank) | Program Document |  | Bank to evaluate Bank Compliance Program document for enhancements needed to incorporate S1 | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Reg B |  | Evaluate S1 definition of application and completed application to determine if changes are required. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg B |  | Bank Compliance will evaluate the Reg B process at S1 and determine any gaps and updates that will be necessary. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg B |  | Conduct Reg B Gap Analysis with S1 and the Bank | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg B |  | Enact any necessary Reg B changes into S1; as identified | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Reg O |  | Bank to determine if any enhancements to the Insider Board Resolution are needed | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Reg O |  | Bank to assist S1 in Implementing procedures and monitoring | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg O |  | Bank to add S1 to distribution list when an insider change is made | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg P |  | Bank to evaluate current sharing practices & policy | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg P |  | Bank to determine updates to the Privacy Notice and SB1 Notices | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reg P |  | Bank to determine Opt Out tracking via affiliate definition (California SB1) | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Regulation O |  | Determine a list of key employees from S1 that will need to be incorporated into the weekly report query comparison by the Bank. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Regulatory Change Management |  | Ensure impacted stakeholders, process impacts, communication of changes, and monitoring of implementation is documented | Jessica Staudt |  | Optimization | 2018-07-01 | 2019-01-01
Compliance 2nd LOD (Bank) | Remediation |  | Verify any compliance review issues have been remediated by following the Bank Compliance Dept. program. Report up through Management Compliance Committee. |  |  | Optimization | 2018-10-01 | 2018-12-01
Compliance 2nd LOD (Bank) | Reporting |  | Bank to incorporate S1 into Compliance Board Reporting |  |  | Optimization | 2018-07-01 | 2018-08-01
Compliance 2nd LOD (Bank) | Reporting |  | Determine what reports are utilized today for compliance monitoring, for example Reg B timing is monitored today (The Compliance Group) | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Reporting |  | Bank Compliance will review reporting and provide guidance on the reporting elements and timing | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Reverse Mortgage |  | Bank needs to conduct training specific to Reverse Mortgage in order to have required expertise to conduct reviews. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Reverse Mortgage Product | Reverse Mortgage | Evaluate reverse mortgage testing spreadsheet utilized by Compliance during Due Diligence Phase | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Risk Assessment |  | Bank to evaluate risk assessment and determine enhancements or gaps | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Safe Act (NMLS) |  | Bank to evaluate current Safe Act process; enhance process if necessary | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Social Media and Web Monitoring |  | Bank to evaluate S1 Social Media marketing and compare to Bank's Social Media Policy and Strategy Document | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 2nd LOD (Bank) | Social Media and Web Monitoring |  | Notify Mutual Insurance Company to include S1 within their social media tool "Ensure", that monitors negative news and other web presence | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-10-01
Compliance 2nd LOD (Bank) | Testing - Compliance Reviews |  | Issues identified during initial due diligence will be reviewed for completion by Bank Compliance | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Testing - Compliance Reviews |  | Bank to perform review of Q1 HMDA Data of S1 | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Compliance 2nd LOD (Bank) | Training |  | Bank to utilize S1 training attendance log for monthly tracking in the master system | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Training | Reverse Mortgage | Bank to determine training needs for reverse mortgage within MOOB | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Training |  | Bank to evaluate trainings within Knowledge Coop to determine if sufficient for all elements including regulatory | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Training |  | Bank to determine best approach for rolling out training deemed necessary by the Bank | Jessica Staudt |  | Optimization | 2018-07-01 | 2018-09-01
Compliance 2nd LOD (Bank) | Training |  | Bank to assign training deemed necessary; outside of S1's current training schedule | Jessica Staudt |  | Optimization | 2018-10-01 | 2018-11-01
CRA | Reporting |  | Determine S1 assessment areas "LPO or REMAs" and how those affect the Bank's assessment areas | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | In/Out Assessment Area |  | Determine CRA definition of "affiliate" | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | In/Out Assessment Area |  | Determine in/out ratio for S1 (ie how wholy owned sub that is a mortgage lender, portfolio) is counted by the Bank | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | In/Out Assessment Area |  | Conduct risk assessment and gap analysis, in conjunction with bank compliance and Fair Lending Officer | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | In/Out Assessment Area | Reverse Mortgage | Conduct evaluation of peer bank HECM programs | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | Reporting |  | Review S1 product line including; bond, DAPs, and other mortgage specific products. Determine which are CRA applicable. | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | Affiliate Lending |  | Identify if Reg W or CRA Regulatory Requirement | Stephanie Couser |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
CRA | Program |  | Integrate S1 into the Bank's CRA program. | Stephanie Couser |  | Optimization | 2018-10-01 | 2018-01-01
CRA | Reporting |  | Add S1 performance to CRA scorecard, CRA advisory committee, CRA self assessment and CRA board reporting | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-01-01
CRA | Reporting |  | Communicate S1 KPI and Risks to S1 board quarterly | Stephanie Couser |  | Optimization | 2018-10-01 | 2018-01-01
CRA | In/Out Assessment Area |  | Determine additional bank assessment areas and best approach (ie ATM or Brick & Mortar) | Terry Connealy |  | Optimization | 2018-07-01 | 2018-10-01
CRA | In/Out Assessment Area |  | Determine how S1 service areas impact the bank's assessment areas (EX: HECM) | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-10-01
CRA | In/Out Assessment Area |  | Determine if Bank will include S1 loans towards CRA, 2018, 2019, etc. | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-10-01
CRA | Reporting |  | Develop reporting of CRA applicable loans and distribute to Bank CRA Officer on a monthly basis | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-10-01
CRA | Personnel |  | Identify a S1 CRA Liasion | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-10-01 | 0.25
CRA | Strategic Plan |  | Incorporate S1 into the Bank's Strategic and Marketing Plan | Stephanie Couser |  | Optimization | 2018-07-01 | 2019-01-01
CRA | Performance Goals |  | Incorporate S1 into Bank's CRA performance goals | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-10-01
CRA | Guidelines |  | Provide S1 the Bank's CRA product guidelines to incorporate into their existing procedures | Stephanie Couser |  | Optimization | 2018-07-01 | 2019-01-01
CRA | Training |  | Develop framework for CRA training including; videos, and webex. | Stephanie Couser |  | Optimization | 2018-07-01 | 2019-01-01
CRA | Training |  | Conduct annual CRA board training for S1 | Stephanie Couser |  | Optimization | 2018-07-01 | 2019-01-01
CRA | Training |  | Track ongoing CRA training completed by S1 employees | Jessica Staudt |  | Optimization | 2018-07-01 | 2019-01-01
CRA |  |  | Bank to report to the Board of Directors August, 2018 updates on CRA | Stephanie Couser |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Policies |  | Identify any differences between credit policies and procedures | Ed Woolman |  | Optimization | 2018-07-01 | 2018-10-01
Credit Administration | Appendix J |  | Review S1's answers to the questionaire and ensure the answers align to what is expected by the OCC. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Products |  | Complete risk assessment of the Forward product suite for S2, especially the unique product offerings (Alt A, Foreign National, Non-QM, Jumbo, Wholesale) for Safety and Soundness. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Products |  | Complete risk assessment of the Reverse product suite of S1, especially any unique product offerings for Safety and Soundness. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Products |  | Determine if all current product offerings will remain in the suite, or if certain product offerings need to be exited due to Safety and Soundess concerns. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Products |  | If there are any products recommended for removal, what is the potential of impact to employees? | Ed Woolman |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Repurchase Risk by Product Offering |  | The Bank is a buyer of Correspondent Mortgage Loans, and is fully underwriting all loans prior to commiting to purchase. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Delegated and Non-Delegated Lending Authorities |  | Complete risk assessment of all products that S1 has Delegated Lending Authority. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Delegated and Non-Delegated Lending Authorities |  | Determine if the current Delegated Lending Authority should be continued or switched to Non-Delegated. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Exceptions, Escallations, and Exception Tracking |  | Identify any differences between the two entities, and then incorporate alignment. | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Denials |  | S1 to send Denial forms to Bank | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Policies |  | Bank to review credit policies and identify gaps | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Policies |  | Enhance S1 credit policies to include all identified gaps | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Denials | Compliance | Bank to review S1 Denial forms and suggest changes as deemed appropriate | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Lending Authority |  | Bank to supply S1 the Lending Authorities Credit Authority Matrix to implement | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Lending Authority |  | S1 to complete and implement the Credit Authority Matrix lending authorities process to all S1 employees | Ed Woolman |  | Optimization | 2018-07-01 | 2018-08-01
Credit Administration | Notice of Incomplete App |  |  | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Counter Offers |  |  | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Credit Administration | Personnel |  | Bank to assess if additional headcount is needed to support S1 | Ed Woolman |  | Optimization | 2018-07-01 | 2018-09-01
Facilities | Leases/Facilities | Legal | Identify if there are any urgent/expired leases that need immediate attention | Rick Neumeyer | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-06-01
Facilities | Leases/Facilities | Legal | San Diego lease requires change of ownership | Rick Neumeyer | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Leases/Facilities | Legal | Mutual and S1 to provide San Diego landlord proper notice | Rick Neumeyer | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-05-20
Facilities | Leases/Facilities | Legal | S1 to send Mutual all leases | Rick Neumeyer | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Physical Security |  | Mutual to do onsite physical security inspection of S1 San Diego Office | Rick Neumeyer |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Physical Security |  | Post S1 San Diego inspection, Mutual to add physical security enhancements adaquate to Mutual standards. | Rick Neumeyer |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Leases/Facilities |  | Portfolio Manager and Director of Real Estate will compile critical dates list and work with management to decide strategy and help needed to carry out renewals or closures. | Rick Neumeyer |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Leases/Facilities | Legal | S1 is reviewing all lease agreements to see which ones require a notification of ownership change. | Rick Neumeyer |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Facilities | Leases/Facilities |  | Cursory Review of S1 Leases Has Taken Place by MOOB. | Rick Neumeyer |  | Completed | 2018-05-10 | 2018-05-10
Facilities | Security |  | Review all S1 facility locations and ensure adaquate security standards | Rick Neumeyer |  | Optimization | 2018-07-01 | 2019-01-01
Facilities | Personnel | Human Resources | Determine if additional Mutual of Omaha Bank Facilities needs additional staff | Rick Neumeyer |  | Optimization | 2018-07-01 | 2019-01-01 | 1
Facilities | Leases/Facilities | Legal | Bank and S1 to determine best approach for those leases coming for renewals | Rick Neumeyer | Tim Larsen | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities | Legal | Determine if Bank's lease software system can be unlinked to accounts payable in order to enter S1 leases. | Rick Neumeyer | Tim Larsen | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities | Legal | Mutual to check into if the lease system will allow for creation of a separate company. (S1) | Rick Neumeyer | Tim Larsen | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities | Legal | Mutual, or get access for S1, to upload S1 leases into "Visual Lease" | Rick Neumeyer | Tim Larsen | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities |  | Mutual to understand if Mutual AP will take over payment of the leases | Rick Neumeyer |  | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities |  | Mutual to setup meeting with Accounts Payable to determine best lease payment approach. | Rick Neumeyer |  | Optimization | 2018-07-01 | 2019-01-01
Facilities | Leases/Facilities |  | S1 will discuss all leases over $50k, or critical, with Mutual prior to signing leases | Rick Neumeyer |  | Optimization | 2018-07-01 | 2019-01-01
Fair Banking | Risk Appetite |  | Determine S1's own risk appetite/tolerance levels (maintain 0 tolerance discrimination) | Matt Bunting |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Fair Banking | Risk Assessment |  | Incorporate S1 into the Bank's Risk Assessment | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Risk Assessment |  | Obtain Bank board approval on identified risk appetite / tolerance levels | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Risk Assessment |  | Obtain S1 board approval on identified risk appetite / tolerance levels | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Program Document |  | Incorporate S1 into the Fair Banking program document | Matt Bunting |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Fair Banking | Program Document |  | Obtain Bank board approval on Fair Banking Program document | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Program Document |  | Obtain S1 board approval on Fair Banking program document | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Policies |  | Conduct current Fair Banking/UDAAP policy comparison between S1 and Bank | Matt Bunting |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Fair Banking | Policies | UDAAP | S1 to adopt bank UDAAP policy within 30 days | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Policies | Fair Banking Program | Obtain Bank board approval of updated Bank Fair Lending Policy (to include S1) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Policies | UDAAP | Obtain S1 board approval of the Bank's UDAAP policy | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Policies | Forward Mortgage | Compare S1 Fair Lending policy with the Bank Fair Lending Policy | Matt Bunting |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Fair Banking | Policies | Reverse Mortgage | Compare S1 Fair Lending policy with the Bank Fair Lending Policy | Matt Bunting |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
Fair Banking | Policies | Forward Mortgage | Update S1 Fair Lending policy with Bank recommendations | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Policies | Reverse Mortgage | Update S1 Fair Lending policy with Bank recommendations | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Policies |  | Obtain S1 Board Approval for S1 Fair Lending Policies; forward and reverse | Matt Bunting |  | Optimization | 2018-07-01 | 2018-08-01
Fair Banking | Procedures |  | Update existing S1 procedures to include elements of the Bank's Fair Banking program | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Training |  | Communicate Fair Lending procedure program changes to S1 employees | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Oversight |  | Determine S1 credit markets (LPO or # Apps) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Oversight | Forward Mortgage | Determine HMDA data extract from Encompass | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Oversight | Reverse Mortgage | Determine HMDA data extract from Reverse Vision | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Oversight |  | Extract S1 HMDA data to import into Bank Wiz/FLARE | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Oversight |  | Develop FLARE for Risk Management (risk metrics for marketing, Underwriting and pricing) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Test Plan/Testing |  | Determine Risk Management methodology: discretion, Underwriting, Pricing (TALC), Marketing (eligible demographics) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Test Plan/Testing |  | Conduct file reviews as deemed necessary | Matt Bunting |  | Optimization | 2018-07-01 | 2019-01-01
Fair Banking | Test Plan/Testing |  | Determine specific brokerage oversight elements for tracking | Matt Bunting |  | Optimization | 2018-07-01 | 2019-01-01
Fair Banking | Test Plan/Testing |  | Conduct ongoing Quarterly Call monitoring as part of the Bank oversight | Matt Bunting |  | Optimization | 2018-10-01 | 2019-01-01
Fair Banking | Personnel |  | S1 to hire additional staff to support fair banking and UDAAP | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01 | 1
Fair Banking | Reporting |  | Add S1 Fair Banking performance to Bank Board's quarterly FLARE | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Reporting |  | Communicate S1 KPI and Risks to S1 board (monthly or quarterly) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-09-01
Fair Banking | Training |  | Enhance existing S1 Fair Lending training | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Training |  | Track S1 Fair Lending training materials | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Training |  | Track S1 Fair Lending staff attendendance | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Training |  | Provide S1 board specific fair lending training | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Determine if S1 Fair Lending advertising checklist is sufficient | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Develop S1 Fair Lending advertising materials | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Develop S1 Marketing summary sheet to include; what ad, when it ran, in what publication, etc. | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Review S1's state by state advertising disclosures | Matt Bunting |  | Complete | 2018-05-10 | 2018-05-15
Fair Banking | Advertising Review |  | Determine Fair Lending Ad review process (FLOD, SLOD, etc.) | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Determine Fair Lending advertising key tracking elements and volume | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01
Fair Banking | Advertising Review |  | Develop Fair Lending oversight sampling to be conducted by Bank Fair Banking Manager | Matt Bunting |  | Optimization | 2018-10-01 | 2019-01-01
Fair Banking | Personnel |  | Bank to assess adequacy of Fair Lending staffing | Matt Bunting |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
Fair Banking | Personnel |  | S1 to hire additional staff to support Fair Lending Ad reviews | Matt Bunting |  | Optimization | 2018-07-01 | 2018-10-01 | 1
Finance | Financial Reporting |  | S1 to determine roles and responsibilities after purchase specific to call reports, HUD reporting, audited balance sheets, profit loss statements and financial reporting in general | Margie Heller |  | Optimization | 2018-07-01 | 2018-08-01
Human Resources | Policies |  | Compare Code of Ethics policy and processes to adopt most risk adverse option | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare employee termination policy and processes to adopt more risk adverse option | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare recruiting policy and process to adopt most risk adverse option | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare onboarding policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare commissions policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare payroll policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare timesheets policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare HR matters (counseling, harrasment, etc.) policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare compensation agreements policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare bonuses policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare offer letters policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare talent retention policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare succession planning policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare PTO tracking policy (ADP) and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare health insurance and other benefits policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare travel policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare expense reporting policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare garnishment order policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare 401k deposit policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare background check policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare determining additional staffing policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare personnel risk policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | Policies |  | Compare HR training courses (Ethics) policy and processes to adopt most risk adverse action | Roseann Neumeyer | Tim Larsen | Optimization | 2018-10-01 | 2019-01-01
Human Resources | LIcenses |  | Determine which company will handle NMLS onboarding and terminations (considering 2 different tax ID #'s) | Roseann Neumeyer | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Policies |  | Onsite Risk Assessment Meeting at S1 - Conduct information security and technology risk asssessment and gap analysis. Includes brokers, technology, computers, and phones. To be sure they meet necessary Bank knowledge and standards. | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Policies |  | Bank to understand new go forward plan | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Policies |  | Bank to assess what S1 polcies are | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Policies |  | Bank will provide guidance on what the bank would like to see on the Information Security and Technology policy to ensure required elements are implemented | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Policies | Legal | Mutual to provide S1 with the Mutual infromation security and technology policies | Al Palamino | Tim | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Policies |  | Brokers need to have attestation that they will follow the Bank's Information Security Guidelines as outlined in the bank policy | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Staffing |  | Every employee at S1 will receive a company issued laptop | Tate Fitzgerald | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Staffing |  | Does S1 have a Privacy officer - IE Al Palamino is the bank's | Al Palamino | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Information Security | Corporate Website | Marketing | S1 continue to manage corporate website, web hosting and website calculators. However, bank CISO will assess required parameters during onsite risk assessment | Al Palamino | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Corporate Website | Marketing | Model risk management: need to assess what if any, models are used on S1 website today. Incorporate into bank model validation requirements. | Amy Swartwood | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Marketing | Forward Mortgage | Drip Campaigns: evaluate if drip campaign customer communications require privacy policy updates required by Reg P. | Al Palamino | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Marketing | Reverse Mortgage | Drip Campaigns: evaluate if drip campaign customer communications require privacy policy updates required by Reg P. | Al Palamino | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Statements | Reverse Mortgage | Complete Due Diligence Questionnaire on Clink for Revsere Mortgage statement printing; work toward EVMP | John Matuszeski |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | BCP/DR "technology RTOs" |  | Review BCP during onsite due diligence meeting; including BCP/DR policy and program | Al Palamino |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Information Security | Data Storage Capabilities |  | Determine adaquate data storage capabilities including; core systems, general network drives, accounting software, email, network shares, outlook, Office 365, etc. | Tate Fitzgerald |  | Completed | 2018-05-10 | 2018-05-10
Information Security | Policies |  | For S1 policies that do not exist, and are deemed necessary, attestation by S1 to follow the bank's existing policy will be necessary | Al Palamino | Bill Trask | Optimization | 2018-07-01 | 2018-08-01
Information Security | Staffing | Human Resources | Post due diligence, identify if additional IT staff is needed | Al Palamino | Bill Trask | Optimization | 2018-06-10 | 2018-07-10
Information Security | HelpDesk |  | Determine if helpdesk enhancements are necessary for S1 | Tate Fitzgerald | Bill Trask | Optimization | 2018-10-01 | 2019-01-01
Information Security | System Access | Bank Compliance | What systems would bank personnel need access to for bank oversight | Tate Fitzgerald | Tim Larsen | Optimization | 2018-07-01 | 2018-08-01
Information Security | System Access | Bank Compliance | S1 can work with external auditors and bank personnel to get systems access. | Tate Fitzgerald | Tim Larsen | Optimization | 2018-08-01 | 2018-10-01
Information Security | BCP/DR "technology RTOs" |  | Post assessment; integrate S1 into the Bank's BCP/DR programs and tracking | Al Palamino |  | Optimization | 2018-10-01 | 2019-01-01
Information Security | Networks |  | Mutual to conduct network assessment of all S1 offices. Provision networking equipment will enable all boundary/network security controls. Deploy all end point and platform security controls. | Al Palamino |  | Optimization | 2018-07-01 | 2018-10-01
Information Security | Networks |  | Migrate user access provisioning processes to the IDM team | Al Palamino |  | Optimization | 2018-07-01 | 2018-10-01
Information Security | IT Systems Standardization |  | Review network and telecommunication systems and review new purchases to ensure bank standards are adopted (ie firewalls, switches, routers, and security appliances) | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | IT Systems Standardization |  | Review end user devices (laptops, desktops, printers) to ensure consistency with bank standards. Includes brokers. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | IT Systems Standardization |  | Review print and copy devices and contracts to align standardization. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | IT Systems Standardization |  | Update broker contracts to include appropriate language for privacy, security requirements and expectations regarding use of personal devices. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Due Diligence/3rd Parties |  | Mutual to conduct review of Versa. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Due Diligence/3rd Parties |  | Mututal to align with 3rd party IS support to provide direction and oversight regarding how the hardware, network, vendors and systems are delivered and maintained. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Training |  | Determine if S1 Information Security Training is sufficient, Knowledge Coop. Identify and address gaps. | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Training |  | Education on how information security policies and standards will change within S1 | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Training |  | Completion of annual awareness training prior to gaining system access | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Information Security | Training | Human Resources | Mutual will have certain required trainings that we need to identify how to deliver these to S1 employees | Al Palamino |  | Optimization | 2018-05-10 | 2018-10-01
Internal Audit | Independent Audit | BSA/AML | Evaluate need for 2018 review and strategize solution | Russ Hancock |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Internal Audit | Reverse Mortgage |  | Internal Audit needs to conduct training specific to Reverse Mortgage in order to have required expertise to conduct reviews. | Russ Hancock |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Internal Audit | Independent Audit | BSA/AML | Incorporate S1 into 2019 BSA/AML audit to evaluate oversight of S1 and include execution of integration plans | Russ Hancock |  | Optimization | 2018-05-10 | 2019-04-01
Internal Audit | Independent Audit | The Compliance Program | Evaluate need for 2018 review and strategize solution. Consider incorporating S1 into next scheduled fair banking audit - 2018. to evaluate oversight and execution of integration plans. | Russ Hancock |  | Optimization | 2018-05-10 | 2019-01-01
Internal Audit | Independent Audit | Fair Banking Program | Evaluate need for 2018 review and strategize solution. Consider incorporating S1 into next scheduled fair banking audit - 2018. to evaluate oversight and execution of integration plans. | Russ Hancock |  | Optimization | 2018-05-10 | 2019-01-01
Internal Audit | Independent Audit | Independent Testing | Evaluate 2018 audit coverage needs; including areas of compliance, financial, operational, and technology risk. | Russ Hancock |  | Optimization | 2018-05-10 | 2019-01-01
Internal Audit | Independent Audit | Independent Testing | Conduct risk assessment and gap analysis, in conjunction with bank compliance. | Russ Hancock |  | Optimization | 2018-05-10 | 2019-01-01
Internal Audit | Independent Audit | Independent Testing | Evaluate 2018 audit resource needs; including areas of compliance, financial, operational, and technology risk. | Russ Hancock |  | Optimization | 2018-05-10 | 2019-01-01 | 1
Legal | Leases/Facilities | Legal | Understand facility leases and how it impacts state regulatory licenses | Gene Twellman | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Contract Reviews |  | S1 to evaluate their current legal contracts and make a recommendation $ amount/criticality for when to engage Mutual's legal team for contract renewals, Mortgage Loan Purchase Agreements, facilities leases, and adding of investors. ($50k was discussed) | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Contract Reviews |  | S1 to categorize critcal contracts/importance to operations | Anne Stockman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Contract Reviews |  | Mutual to take renewals and plug in provisions during amendment phase | Anne Stockman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Regulatory Exams/Issues |  | Receive OCC approval, all necessary state regulatory approvals | Anne Stockman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Regulatory Exams/Issues |  | Determine which states we will be allowed exemptions in | Anne Stockman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Regulatory Exams/Issues |  | Determine how to handle post close state regulatory exams | Anne Stockman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Leases/Facilities | Facilities | Understand how Mutual and S1 will coordinate NMLS system and leases | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Corporate Governance |  | All S1 board and officer meetings, resolutions, and other corporate governance matters shall be handled by bank law group and office of the corporate secretary | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Litigation Management |  | Transition litigation management over to Mutual of Omaha Bank law group | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Litigation Management |  | Complete review of all litigations for S1 | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Litigation Management |  | Ensure all existing and new litigation matters including subpoenas are entered into the bank's litigation records | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Legal | Policies | Bank Compliance | Obtain inventory of all S1 policies; both regular and enterprise | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10
Legal | Policies | Bank Compliance | Evaluate legal staff and determine if additional staff is needed, Hire as needed | Gene Twellman | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-06-10 | 1
Legal | Regulatory Exams/Issues |  | Review all regulatory exams | Anne Stockman | Bill Trask | Completed | 2018-05-10 | 2018-05-10
Legal | Licenses |  | S1 continue to track state licensing; until transition | Anne Stockman | Bill Trask | Completed | 2018-05-10 | 2018-05-10
Legal | Contract Reviews |  | Review S1 critical contracts | Gene Twellman | Bill Trask | Optimization | 2018-07-01 | 2018-10-01
Legal | Contract Reviews |  | Post contract review; understand if there are any contracts we can terminate due to duplicity | Gene Twellman | Bill Trask | Optimization | 2018-10-01 | 2018-11-01
Legal | Licenses |  | Transition of active state licensing | Anne Stockman | Bill Trask | Optimization | 2018-07-01 | 2019-01-01
Legal | Policies | Bank Compliance | Review Bank and S1 policies to ensure coverage of all pertinent areas. This includes; regular and enterprise policies. | Gene Twellman | Bill Trask | Optimization | 2018-06-10 | 2018-10-01
Legal | Policies | Bank Compliance | Identify streamlining language within S1 to mirror Bank's policy standardization. | Gene Twellman | Bill Trask | Optimization | 2018-05-10 | 2018-10-01
Legal | Policies | Bank Compliance | Adopt revisions or additional policies as necessary | Gene Twellman | Bill Trask | Optimization | 2018-05-10 | 2018-10-01
Legal | Policies | Bank Compliance | Determine which policies will be adopted, which will solely live at S1 and which will have dual sets at each | Gene Twellman | Bill Trask | Optimization | 2018-05-10 | 2018-10-01
Legal | Policies | Bank Compliance | Obtain Mutual of Omaha Bank board approval of all new policies (submit to November bank board meeting) | Gene Twellman | Bill Trask | Optimization | 2018-05-10 | 2018-10-01
Legal | Policies |  | Communicate all policy changes to S1 staff and educate on how this impacts the way they work | Gene Twellman | Bill Trask | Optimization | 2018-07-01 | 2018-10-01
Legal | Policies | Information Security | Establish governance of S1 documentation and policies regarding Information Security and Technology | Gene Twellman | Bill Trask | Optimization | 2018-07-01 | 2018-10-01
Legal | Domain Registrations |  | Determine how S1 domains will be tracked and transitioned to the bank, if applicable | Amber |  | Optimization | 2018-10-01 | 2019-01-01
Legal | Policies | Legal | Determine if inclusion of S1 will trigger changes to the bank's policy. If yes, update policy and get board approval. | Gene Twellman |  | Optimization | 2018-07-01 | 2018-10-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Complete risk assessment of Forward product suite for S1, especially unique products (Alt A and Foreign National, Non QM, Jumbo, Wholesale) / Safety and Soundness | Ed Woolman | N/A | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Complete risk assessment of Reverse product suite for S1, especially unique products (Alt A and Foreign National) / Safety and Soundness | Ed Woolman | N/A | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Have a discussion on if all current products will remain in the suite, or if there are some that need to be exited? If so, when and how? | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Have a discussion on if all current products will remain in the suite, or if there are some that need to be exited? If so, when and how? | Ed Woolman | Cynthia Ferral | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Understand repurchase risk per product (including reps and warranties) | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Understand repurchase risk per product (including reps and warranties) | Ed Woolman | Cynthia Ferral | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Assess: If we remove a product, what is employee impact? | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Assess: If we remove a product, what is employee impact? | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Contractual requirements need assessed for DMI transfers | John Matuszeski |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Identify what each of the S1 investors have for requirements and which loans can be sold where | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Identify what each of the S1 investors have for requirements and which loans can be sold where | Andrew Tetlow |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing | Marketing | Review and assess S1 loan documents, disclosures, and marketing materials to understand any disclaimers. Do we need to update the company name? (adding; "Synergy One Lending Inc, a Mutual of Omaha Bank Company" | Joe Rodgers |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing |  | Notify MERS of S1 acquisition | John Matuszeski | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing |  | Notify Freddie Mac of S1 acquisition | John Matuszeski | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing |  | Notify Fannie Mae of S1 acqusition | John Matuszeski | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing |  | S1 to send Mutual Key stakeholder notices for S1's loan processing vendors | Terry Connealy | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Underwriting | Forward Mortgage | Complete an underwriting specific risk assessment to include process on pricing exceptions, approval and oversight, as well as underwriting specific QA/QC | Ed Woolman | Cynthia Ferral | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Underwriting | Reverse Mortgage | Complete an underwriting specific risk assessment to include process on pricing exceptions, approval and oversight, as well as underwriting specific QA/QC | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Underwriting | Reverse Mortgage | Understanding of national certifications for reserve mortage originations | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Underwriting | Reverse Mortgage | Understanding of underwriter certification requirements | Ed Woolman | Joe Teravossy | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Reverse Mortgage | Identify and hire a QA person for Reverse | Jessica Staudt | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Forward Mortgage | Identify and hire a QA person for Forward | Jessica Staudt | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Forward Mortgage | Understand what the hard stops are already built into the Encompass system and what are the gaps? Validate the hard stops are accurate. Will the system satisfy, or do we require a resource | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Reverse Mortgage | Understand what the hard stops are already built into the Reverse Vision system and what are the gaps? Validate the hard stops are accurate. Will the system satisfy, or do we require a resource | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Forward Mortgage | Coordinate with Bank Compliance to determine QA elements that are needed for Forward | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QA | Reverse Mortgage | Coordinate with Bank Compliance to determine QA elements that are needed for Reverse | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QC | Forward Mortgage | Coordinate with Bank Compliance to determine enhancements of S1 QC | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QC | Reverse Mortgage | Coordinate with Bank Compliance to determine enhancements of S1 QC | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QC |  | S1 will supply Mutual with The Compliance Group's monthly report for review (2 reports; compliance and credit) | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QC | Bank Compliance | Determine if The Compliance Group monthly review will suffice, or if TENA will need to be engaged | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | QC | Bank Compliance | Need to add internal 10% review of The Compliance Group work as oversight. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Closing | Forward Mortgage | Evaluate current process and procedures for funding and closing checklists to determine if enhancements are needed. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Closing | Reverse Mortgage | Evaluate current process and procedures for funding and closing checklists to determine if enhancements are needed. | Jessica Staudt |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Processing | Bank Compliance | Evaluate current processing procedures and checklists to determine if enhancements are needed. | Jessica Staudt |  | Completed | 2018-05-10 | 2018-05-15
Loan Origination, Underwriting, Loan Closing, QA & QC | Underwriting |  | OCC Appendix J to be completed by S1 | Ed Woolman | David Entrekin | Completed | 2018-05-05 | 2018-05-09
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Need to establish a timeframe of when we expect to start purchasing and servicing loans | Andrew Tetlow |  | Optimization | 2019-01-01 | 2019-06-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Need to establish a timeframe of when we expect to start purchasing and servicing loans | Andrew Tetlow |  | Optimization | 2019-01-01 | 2019-06-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Transfer 75+ servicing loans from S1 to Mutual's servicing team (DMI requires 45 day notice) | John Matuszeski |  | Optimization | 2018-10-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Determine how the process of delivering S1 loans directly to DMI would look going forward. | John Matuszeski |  | Optimization | 2018-10-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Mutual to investigate how we would purchase servicing rights of reverse mortgages | John Matuszeski |  | Optimization | 2018-10-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels |  | Understand how and when to merge Mutual of Omaha Mortgage centralized and retail teams with S1 | Terry Connealy | David Entrekin | Optimization | 2018-07-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Application | Forward Mortgage | Assess process to see if there are any regulatory and/or process gaps that need addressed | Jessica Staudt | David Entrekin | Optimization | 2018-07-01 | 2018-11-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Application | Reverse Mortgage | Assess process to see if there are any regulatory and/or process gaps that need addressed | Jessica Staudt | David Entrekin | Optimization | 2018-07-01 | 2018-11-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Forward Mortgage | Mutual needs to address servicing rights for Forward: Retail, DTC, Broker, and SG Captial | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Loan Product/Channels | Reverse Mortgage | Mutual needs to address servicing rights for Reverse: Hybrid Correspondent, Retail, Broker/Wholesale (3rd party originations) and DTC | Andrew Tetlow |  | Optimization | 2018-07-01 | 2019-01-01
Loan Origination, Underwriting, Loan Closing, QA & QC | Correspondent |  | Assessment of Encompass loan origination platform / Comergence platforms specific to correspondent loan purchases | John Matuszeski |  | TBD | 2018-10-01 | 2019-01-01
Loan Review | Risk Assessment |  | Incorporate S1 into Bank's Risk Assessment | Harry Goudling |  | Optimization | 2018-07-01 | 2018-10-01
Loan Review | Personnel |  | Evaluate 2019 resources necessary for annual risk assessment and loan review plan prep | Harry Goudling |  | Optimization | 2019-01-01 | 2019-02-01 | 1
Loan Review | Procedures |  | Complete procedures to support the loan review plan | Harry Goudling |  | Optimization | 2018-07-01 | 2018-10-01
Loan Review | Independent Testing |  | Incorporate S1 into the next scheduled Mortgage Banking Loan Review | Harry Goudling |  | Optimization | 2018-07-01 | 2018-01-01
Model Risk Management "MRM" | Policies | Ops Risk | Assess and capture all S1 models | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Model Risk Management "MRM" | Testing | Ops Risk | S1 to assign model owners to each model; to complete a model validation questionnaire each year | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Model Risk Management "MRM" | Program | Ops Risk | Adopt shared service MRM program | Marty Froelick |  | Optimization | 2018-07-01 | 2018-09-01
Model Risk Management "MRM" | Policies | Ops Risk | Adopt the Bank's MRM policy | Marty Froelick |  | Optimization | 2018-07-01 | 2018-09-01
Model Risk Management "MRM" | Testing | Ops Risk | Adopt MRM testing standards including all MRM life cycle stages | Marty Froelick |  | Optimization | 2018-07-01 | 2018-09-01
Model Risk Management "MRM" | Training |  | shared service to conduct annual MRM training for S1 | Marty Froelick |  | Optimization | 2019-01-01 | 2019-03-01
Model Risk Management "MRM" | Personnel |  | Identify a primary MRM person at S1 | Marty Froelick |  | Optimization | 2018-10-01 | 2019-01-01 | 1
Model Risk Management "MRM" | Reporting |  | Develop reporting from Open Pages, same as the bank, for management reporting committee | Marty Froelick |  | Optimization | 2018-07-01 | 2018-08-01
Operational Risk | Program |  | Identify a representative for S1 and add them to the monthly bank Operations Risk Management Committee | Reid Adamson |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Operational Risk | Policies |  | Mutual of Omaha Bank to provide a copy of the Bank Operations Risk Policy to S1 | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Operational Risk | Reporting |  | Determine what type of operational risk reporting S1 uses today and assess for gaps | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Operational Risk | Reporting |  | KRIs and scorecards for monitoring and reporting to uppper management specific to operational risk | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Operational Risk | Model Risk Oversight |  | Operational risk conducts oversight and escalation for model validation. | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Operational Risk | Program |  | Incorporate S1 into the bank's Operational Risk Management program. | Marty Froelick |  | Optimization | 2018-10-01 | 2018-01-01
Operational Risk | Program |  | Identify a liasion at S1 to work directly with the bank regarding Ops risk program | Marty Froelick | Bill Trask | Optimization | 2018-07-01 | 2018-08-01 | 1
Operational Risk | Program |  | Oversight by the bank's Operation risk management committee | Marty Froelick | Bill Trask | Optimization | 2018-06-01 | 2018-07-01
Operational Risk | Program |  | Mutual of Omaha Bank to provide a copy of the Bank Operations Risk Program to S1 | Marty Froelick | Bill Trask | Optimization | 2018-05-10 | 2018-06-01
Operational Risk | BCP/DR "process RTO's" |  | Review S1 BCP / DR program, policy and process. Conduct gap analysis. | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
Operational Risk | BCP/DR "process RTO's" |  | Determine if transition of BCP/DR into Bank's program is necessary | Stacey Doty |  | Optimization | 2018-12-01 | 2019-01-01
Operational Risk | New Products & Services |  | Assess S1 New products and services procedure and identify gaps | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
Operational Risk | New Products & Services |  | Idenify Bank oversight elements specific to S1 new products and services procedure | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
Operational Risk | Counter Party Risk |  | Determine overall counter party risk for S1 | Terry Connealy | Bill Trask | Optimization | 2018-05-10 | 2018-09-01
Operational Risk | Insurance |  | Review S1 insurance policy / binder coverage and initiate plan to cancel/replace/amend where necessary | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
REVS | Appraisal Reviews |  | Clarify which loans qualify for exemption to Interagency Guidelines (IAG). | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Clarify which GSE loans are at risk for repurchase and would benefit from REVS review. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | The Bank must seek guidance from OCC on review exemptions, specifically, whether or not reps and warrants for GSE compliance on loans sold to other banks qualify for exemption. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Although GSE sold and insured loans are exempt, it would be prudent to establish a procedure to review appraisals for loans that have high repurchase risk. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Bank vs Non Bank is a quick determinator, Clear Capital for Jumbo's, non prime, Fannie Freddie, ect... use the purchase contracts to see if there is any specifics on exemptions. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Research guidance and follow up with bank counsel to verify | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Bank REVS will put together a summary document identifying which loans are in and which are exempt. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Policies |  | The Bank must determine whether or not S1 should create and maintain a separate policy with REVS oversight or incorporate S1 into existing Bank policy. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Policies |  | S1 will determine if there are any references to appraisals in their existing policies. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Policies |  | REVS will provide copies of the existing bank policy/procedurs to S1 | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Policies |  | REVS will review and approve all S1 appraisal policy and procedures as an oversite element. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Procedures, Checklists, Job Aids & Forms |  | S1 needs to determine which of their procedures include elements of real estate appraisals and evaluations. The procedures should elaborate and expand on the requirements set forth in policy. Among other topics, the procedures should provide requirements for communication with appraisers, what type of valuation product is needed, the useful life of an appraisal, how to order an appraisal or evaluation, and the processes for appraisal and evaluation reviews. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Procedures, Checklists, Job Aids & Forms |  | S1 also needs forms for appraisal reviews and appraisal reconsiderations (disputes, appeals, etc.) | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Procedures, Checklists, Job Aids & Forms |  | REVS would like to review the AMC forms used by S1 today. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Bank Oversight of S1 Appraisal Process |  | REVS needs to determine what specific appraisal elements require direct oversight and also how they are going to actively track and report that oversight to upper management and/or the board | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Customary and Reasonable Fees |  | S1 must establish and periodically update a fee schedule for valuation services. Fee data from AMCs should not be relied upon in creating this schedule. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Customary and Reasonable Fees |  | S1 should engage AMCs using a "cost plus" model where the management fee paid to the AMC is separate from the fee paid to the appraiser and static. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Customary and Reasonable Fees |  | A procedure for fee negotiation due to assignment complexity and rush service should be in place. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Customary and Reasonable Fees |  | AMCs should be regularly audited to ensure timely payment to appraisers. S1 could help ensure timely payment by paying the AMC's directly for their services, rather than requiring the borrower to do so. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Customary and Reasonable Fees |  | The Bank should seek guidance on S1's process of having the borrower pay valuation service providers directly. This is not common practice. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Program |  | S1 to send Mutual formal documentation on the REVS review process, considerations, fees, etc. | James Worden |  | Prior to Day 1 | 2018-05-10
REVS | Program |  | Mutual to review S1's formal REVS process in detail | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Program |  | Post S1 REVS document review; Mutual to identify if S1 REVS program rolls into Bank, or maintains separate | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Guidelines |  | Mutual to investigate and understand what is exempt and what is not to determine scalability | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Guidelines |  | Mutual to understand investors (banks vs. non banks) RE: identifying expectations | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines |  | Interagency guidelines must be interpreted asap | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines | Oversight of 3rd Party Service Providers | Determine what and how Clear Capital can fill gaps, CDA as stop gap/tracking appraisals | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines |  | Mutual to determine what will fall under REVS | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines |  | Mutual to create a matrix of exempt vs. non exempt, and include questionable ones | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines |  | S1 to explain banks vs. non banks | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Guidelines |  | Mutual and S1 to discuss exempt vs non exempt with Outside Counsel | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Policies |  | Mutual to send S1 our REVS policy so they can begin to tailor S1's | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Policies |  | S1 to have their own REVS Policy | James Worden |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
REVS | Policies |  | S1 will go through the guidelines and check appraisal section | James Worden |  | Prior to Day 1 | 2018-06-01 | 2018-07-01
REVS | Procedures |  | S1 to send Mutual a list of AMC forms | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Valuation Independence |  | Mutual to investigate S1 processors ordering of appraisals, dedicated coordinators to place orders, utilizing Mutual's existing staff, adding S1 employees as coordinators within the REVS system | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Oversight of 3rd Party Service Providers |  | S1 review potential for S1 appraisal desk to expand duties; train on REVS process, order, selection of appraisal, etc. | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Oversight of 3rd Party Service Providers |  | Mutual to identify tracking platform for S1 REVS | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Appraisal Reviews |  | Mutual to identify what needs to be reviewed | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Training |  | Mutual and S1 to evaluate who needs to receive adaquate training for those employees completing appraisal reviews | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Oversight of 3rd Party Service Providers |  | EVMP Process for AMC's, including DDQ | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
REVS | Bank Oversight of S1 Appraisal Process |  | Mutual REVS to determine appraisal elements that require oversight and how to report that | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Program |  | Onsite Risk Assessment Meeting at S1 - full review of REVS | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Customary and Reasonable Fees |  | Mutual to provide S1 with customary and reasonable fees | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Customary and Reasonable Fees |  | Mutual REVS to review borrower pay appraisal fees directly | James Worden |  | Prior to Day 1 | 2018-05-10 | 2018-06-01
REVS | Policies |  | S1 needs a policy for real estate appraisals and evaluations; stand alone or incorporated into existing credit/underwriting policy. Containing; all same standards as REVS | James Worden |  | Optimization | 2018-07-01 | 2018-10-01
REVS | Oversight of 3rd Party Service Providers |  | S1 needs to develop an oversight program for its valuation service providers. This includes boarding/vetting procedures, establishing and reporting quality and service metrics, and procedures for exclusion and mandatory reporting. | James Worden |  | Optimization | 2018-07-01 | 2019-01-01
REVS | Personnel |  | Evaluate if additional FTE's are necessary to have proper oversight responsibility | James Worden |  | Optimization | 2018-07-01 | 2018-08-01 | 1
REVS | Personnel |  | Mutual to hire 2 additional reviewers | James Worden |  | Optimization | 2018-07-01 | 2018-08-01 | 2
REVS | Policies |  | S1 to implement REVS policy to S1 | James Worden |  | Optimization | 2018-07-01 | 2018-08-01
REVS | Training |  | S1 to train S1 employees on REVS policy | James Worden |  | Optimization | 2018-07-01 | 2018-08-01
REVS | Communication |  | S1 to communicate REVS policy to all associates | James Worden |  | Optimization | 2018-07-01 | 2018-08-01
Vendor Management | Policies | EVMP | S1 to adopt Mutual's vendor management policy | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Vendor Management | Vendor Reporting | EVMP | S1 to provide a complete list of active vendors | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Vendor Management | Vendor Reporting | EVMP | S1 to assign vendor ownership to all active vendors | Marty Froelick | Bill Trask | Prior to Day 1 | 2018-05-10 | 2018-07-01
Vendor Management | Vendor Reporting | EVMP | Identify the top 30 critical vendors to begin EVMP process | Marty Froelick |  | Prior to Day 1 | 2018-05-10 | 2018-07-01
Vendor Management | Vendor Reporting | EVMP | Determine if additional Bank/EVMP resource is necessary outside of Nick Peterson | Kelsey Perlinger |  | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Vendor Management | Personnel |  | OFAC conducted on new S1 employees needs to be entered in the employee permanent HR file | Vinay Madar |  | Prior to Day 1 | 2018-05-10 | 2018-07-01 | 1
Vendor Management | Escalation | EVMP | Incorporate S1 into remediation/escalation process followed by Bank/EVMP | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
Vendor Management | Program | Legal | S1 to adopt bank / EVMP program | Marty Froelick |  | Optimization | 2018-07-01 | 2018-10-01
Vendor Management | Vendor Reporting | EVMP | S1 assigned vendor owners to complete EVMP matrix for top 30 critical vendors | Kelsey Perlinger |  | Optimization | 2018-07-01 | 2018-10-01
Vendor Management | Vendor Reporting | EVMP | S1 to complete EVMP matrix on remaining vendors (post 31+ active vendors) | Kelsey Perlinger |  | Optimization | 2018-10-01 | 2019-01-01
Vendor Management | Vendor Reporting | EVMP | Identify S1 vendor management watch list and incorporate into Operations Risk Committee Reporting | Marty Froelick |  | Optimization | 2018-10-01 | 2019-01-01
Vendor Management | Vendor Reporting | Ops Risk | EVMP to establish monthly vendor reporting and distribute to S1 (upcoming renewals, watch list, due) | Kelsey Perlinger |  | Optimization | 2018-07-01 | 1//2019
Vendor Management | Vendor Reporting | EVMP | Mutual and S1 to conduct ongoing collaboration with EVMP on vendor reviews going forward | Marty Froelick |  | Optimization | 2018-07-01 | 1//2019
Vendor Management | Vendor Reporting | EVMP | S1 to identify an internal resource to work with EVMP (Liasion) | Kelsey Perlinger |  | Optimization | 2018-07-01 | 2018-10-01 | 1
Vendor Management | Vendor Reporting | EVMP | EVMP to review completed matrices, and identify insufficient due diligence, issues or concerns. Escalate as deemed necessary. | Kelsey Perlinger |  | Optimization | 2018-10-01 | 2019-01-01
Vendor Management | EVMP |  | S1 to inventory all vendor management documentation and provide to Bank. | Kelsey Perlinger |  | Optimization | 2018-07-01 | 2018-09-01
Vendor Management | EVMP |  | EVMP to perform gap analysis of additional vendor management documentation needs | Kelsey Perlinger |  | Optimization | 2018-07-01 | 2018-09-01
Bank to review S1 denial process and ensure it aligns with the Bank
If gaps are identified with the denial process, then S1 to implement updated Denial process
Human Resources | Policies |  | Implement Code of Ethics to S1 employees | Roseann Neumeyer | Tim Larsen | Prior to Day 1 | 2018-05-10 | 2018-07-01

## Tasks
# | Business Unit | Task | Task Description | Company Resources | Owner / Stakeholder | Original Start Date | Projected End Date | Actual Completion Date | Status | Action Items / Issues / Next Steps | Links / Additional Guidance
1 | Compliance / ACH Operations | Implement NACHA Company Entry Descriptions | Configure and enforce required Company Entry Descriptions: PAYROLL (PPD wage/salary credits) and PURCHASE (consumer-authorized e-commerce purchases per NACHA-defined exceptions). Enable validation and reporting. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; IT Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Update mapping/ETL and UI labels; - Add controls to prevent noncompliant descriptions; - Coordinate early adoption communications to originators. | NACHA 2026 Rule Changes
2 | Compliance / ACH Operations | Phase 1 – ACH Fraud Monitoring (ODFIs) | Implement risk-based fraud monitoring for all ODFI activities and for non-consumer Originators/TPSPs/TPSs with 2023 origination volume ≥ 6M. Expand beyond WEB/Micro-Entries to deception-enabled “authorized” payments (e.g., BEC, vendor impersonation, payroll diversion). Document procedures and escalation paths; schedule annual review. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Parameterize alerts for new receivers and sudden account changes; - Establish risk-based processes and procedures that are reasonably intended to identify Entries that are suspected of being unauthorized entries or authorized under "false pretenses; - Enforce dual-control on account changes and approvals; - Remove “commercially reasonable” language from policies. | Phase 1 Link
3 | Compliance / ACH Operations | Phase 1 – ACH Credit Monitoring (RDFIs) | Implement risk-based monitoring of inbound ACH credits for RDFIs with 2023 annual receipt volume ≥ 10M. Align flags/thresholds with enterprise fraud risk framework and case management. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Define anomaly detection scenarios; - Integrate with existing monitoring tooling and reporting; - Establish escalation SLAs (e.g., process for excalating unresolved issues to higher levels of support or authority when current team is unable to resolve). | Phase 1 Link
4 | Compliance / ACH Operations | Phase 2 – Extend Monitoring to All Remaining Parties | Apply ACH Fraud Monitoring to all remaining non-consumer Originators, TPSPs, and TPSs; apply ACH Credit Monitoring to all remaining RDFIs not covered by Phase 1. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-06-22 |  | Not Started | - Confirm population and scope; - Complete testing and sign-off prior to cutover; - Validate reporting and dashboards. | Phase 2 Link
5 | Compliance / ACH Operations | Update Policies / Procedures / Processes | Publish risk-based fraud/credit monitoring procedures; formalize annual review cadence; update data handling, dual-control, and account change verification procedures | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Draft procedure docs and escalation flow; - Refer to RMAG Guidance on ODFI Credit-Push Fraud Response Checklists for assistance; | Link to RMAG Guidance here.
6 | Compliance / ACH Operations | Provide Staff Training | Develop and deliver targeted staff training on social engineering and verification expectations. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance; HR |  | 2026-03-13 |  | Not Started | - Schedule training; - Record attestations.
7 | Compliance / ACH Operations | Update Originator/Third-Party Agreements & ODFI Oversight | Review and update agreements with Originators and Third Parties to reflect new monitoring expectations and ODFI oversight duties. Ensure documentation evidences compliant procedures at Third Parties. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Contract review with Legal and Vendor Mgmt; - Capture attestations and due diligence artifacts; - Update onboarding checklists.
8 | Compliance / ACH Operations | Communications & Cutover Readiness | Notify ACH Operations and Treasury Management of cutover dates; publish client/partner communications on Company Entry Descriptions and monitoring expectations; confirm readiness checkpoints prior to Mar 20 and Jun 22, 2026. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance (Second Line) |  | 2026-03-20 |  | Not Started | - Draft internal/external comms; - Confirm helpdesk scripts; - Final go/no-go checklist.
9 | Compliance / ACH Operations | Annual Review of Fraud Monitoring processes and procedures | Schedule annual review of implemented risk-based fraud monitoring for all ODFI / Originators / TPSPs / TPSs with documented procedures and escalation paths and for inbound ACH credits for RDFIs. | ACH Ops, Treasury Mgmt, InfoSec, Third-Party Mgmt | ACH Operations Manager; Compliance; HR |  | 2027-03-20 |  | Not Started | - Review processes and procedures; - Update processes and procedures to address any evoving risks; - Train staff on any changes to processes and procedures.
10 | Compliance / ACH Operations | Funds Availability Rule for non-Same Day ACH credits | Implement Funds Availability Rule for non–Same Day ACH credits” Update posting schedules (9:00 a.m. local time availability) Adjust for 6:00 a.m. ET ACH Operator file Update core configurations Update disclosures & Ops procedures | ACH Ops, Core Systems, Compliance, Deposit Operations | ACH Ops, Compliance |  | 2026-09-18 |  | Not Started | -Update core job schedules to ensure non–Same Day ACH credits post before 9:00 a.m. local time on Settlement Date. -Validate processing of the 6:00 a.m. ET ACH Operator file and adjust early‑morning sequences accordingly. -Revise posting procedures and disclosures (Deposit Ops + Compliance) to reflect new availability timing.
11 | Compliance / ACH Operations | Update IAT Definition | Update IAT classification logic, onboarding, agreements, and exception processing per revised IAT definition | ACH Ops, Compliance, Treasury Management, BSA/AML | ACH Ops, Compliance, Treasury Management |  | 2026-09-18 |  | Not Started | -Update IAT classification logic in ACH systems to match NACHA’s new definition and ensure IATs cannot be Same Day entries. -Review onboarding and exception workflows (ACH Ops, Treasury, BSA/AML) to ensure correct identification and handling of cross‑border activity. -Confirm third‑party vendors and processors are correctly identifying and flagging IATs under the revised rules.
Note on E2: Sarah Smith: -Contact for questions -Policies or procedures to reference -Vendor Contact
Note on J2: Sarah Smith: -Not Started -In Process -Completed